## BOM change form
BOM Change Form
Form NO： | ECN163224X-E | [5 empty] | SO NO. | 7012441 |  |  |  | Project Name: | 福州福晶科技股份有限公司增容配电工程
Application/Date | l李苏生 | 2018-07-18 17:05 |  | Approve/Date | l刘丽娜 | 2018-07-18 17:11
Add or Cancel 增加或减少 | cubical/drawer/Busway No. | Des. 柜子描述 | MO No. 生产订单号 | Material No. 物料号 | Qty 数量 | Operation Code 工段号 | Attribute 物料属性 | Bin 库位 | Total Qty | Change Reason 变更原因 | Position 位置 | Sub-contract or not 是否外包 | MO release to WS 生产订单是否下达车间 | Change Impact 变更影响 | Material Des.物料描述
Delete | AODX004315 | FZFJ/12M/NSX400H/3P/CT400/Drawer | 124054524 | 33682 | 1 | 200 | PK | 2 | 2 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Add | AODX004315 | FZFJ/12M/NSX400H/3P/CT400/Drawer | 124054524 | P033682 | 1 | 200 | PK | 2 | 2 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Delete | AODX004314 | FZFJ/12M/NSX630H/3P/CT500/Drawer | 124054343 | 33682 | 1 | 200 | PK | 4 | 4 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Add | AODX004314 | FZFJ/12M/NSX630H/3P/CT500/Drawer | 124054343 | P033682 | 1 | 200 | PK | 4 | 4 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Delete | AODX004313 | FZFJ/8M/NSX250H/3P/CT250/Drawer | 124054342 | 33682 | 1 | 200 | PK | 3 | 3 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Add | AODX004313 | FZFJ/8M/NSX250H/3P/CT250/Drawer | 124054342 | P033682 | 1 | 200 | PK | 3 | 3 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Delete | AODX004312 | FZFJ/12M/NSX630H/3P/CT600/Drawer | 124054341 | 33682 | 1 | 200 | PK | 6 | 6 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Add | AODX004312 | FZFJ/12M/NSX630H/3P/CT600/Drawer | 124054341 | P033682 | 1 | 200 | PK | 6 | 6 | 物料替代 | Moved |  | Not | 5位数物料号没法单独下订单 | ADJUSTABLE DELAY UNIT FOR MN 200/250 VAC
Note: Add or Cancel define | [6 empty] | Attribute define |  |  | Reason define:
01: Add material | [6 empty] | C PK: Common Pick |  |  | 客户变更 | Position | Subcontract | MO rel.to WS
02: Delete material | [6 empty] | P PK: Project PK |  |  | 机械设计 | Fixed | Yes | Yes
[7 empty] | BF: Backflush |  |  | 电气设计 | Moved | Not | Not
[7 empty] | BK: Bulk |  |  | 转换文件
车间安装
物料替代
相关部门
其它
Note on L5: SESA59568: Design input this column
Note on M5: SESA59568: Procurement input this column
Note on N5: SESA59568: Procurement input this column
Note on F44: Author: 2 for PCC

## BOM_temp (hidden)
Phantom | Cubicle | Ref | Qty
GHQ10830 |  | 0469200802 | 16
GHQ10854 |  | 0469201002 | 16 |  | Sum of Qty
GHQ10842 |  | 0469200902 | 16 | Cub_Ref | Cubicle | Ref | Total
GHQ10842 |  | 0469200902 | 16 | (blank) | (blank) | 0469200802 | 64
GHQ10842 |  | 0469200902 | 16 | (blank) |  | 0469201002 | 16
GHQ10842 |  | 0469200902 | 16 | (blank) |  | 0469200902 | 240
GHQ10842 |  | 0469200902 | 16 | (blank) |  | 0469208402 | 8
GHQ10830 |  | 0469200802 | 16 | (blank)
GHQ10842 |  | 0469200902 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10830 |  | 0469200802 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10830 |  | 0469200802 | 16
GHQ10842 |  | 0469200902 | 16
GHQ10842 |  | 0469200902 | 16
GHQ11039 |  | 0469208402 | 4
GHQ11039 |  | 0469208402 | 4

## Report
Cubicle | Phantoms list | Variance | Total | (All)
| GHQ10830 | 1
| GHQ10854 | 1 | Sum of Total
| GHQ10842 | 1 | Cub_Ref | Ref | Total
| GHQ10842 | 1 | (blank) | (blank)
| GHQ10842 | 1 | (blank) | (blank)
| GHQ10842 | 1 |  | 0469200802 | 64
| GHQ10842 | 1 |  | 0469201002 | 16
| GHQ10830 | 1 |  | 0469200902 | 240
| GHQ10842 | 1 |  | 0469208402 | 8
| GHQ10842 | 1
| GHQ10830 | 1
| GHQ10842 | 1
| GHQ10842 | 1
| GHQ10842 | 1
| GHQ10842 | 1
| GHQ10842 | 1
| GHQ10842 | 1
| GHQ10830 | 1
| GHQ10842 | 1
| GHQ10842 | 1
| GHQ11039 | 1
| GHQ11039 | 1